# Project Plan — Cluedo (Team 53, G6046)

## 1. Overview

Watson Games asked for a digital version of their Clue! board game with a Pygame GUI, 3–6 players, the full suggestion / refutation / accusation loop, the standard tile-based grid + dice movement, and an autonomous-player option. We delivered all of these as MVP across four sprints between 23 February and 29 April 2026 — see ADR-006 in docs/decisions.md for the Sprint 2 midpoint decision to keep grid + dice and AI in scope rather than descope them.

## 2. Team and roles

| Member | Role | Primary responsibilities |
| --- | --- | --- |
| Floyd | Technical Lead & Integrator | Architecture, Pygame integration, integration testing, code review |
| Maysarah | Game Logic Engineer | Engine, models, deck, game rules |
| Adam | Scrum Master, Documentation Lead & Product Owner | Meetings, documentation, requirements, submission |
| Nasser | UI/GUI Engineer | Pygame screens, components, visual layout |
| Abdurrahman | QA Lead | Unit test suite, regression, system test execution |

## 3. Sprint schedule

| Sprint | Window | Length | Goal |
| --- | --- | --- | --- |
| 1 | 2026-02-23 → 2026-03-08 | 14 days | Foundation: models, deck, engine core, repo, Pygame skeleton |
| 2 | 2026-03-09 → 2026-03-29 | 21 days | Core gameplay + Pygame screens + grid/dice movement (extended one week at midpoint after the keep-in-scope decision on grid + dice / AI — ADR-006) |
| 3 | 2026-03-30 → 2026-04-12 | 14 days | Robustness, validation, F12 token-position fix, AI player module |
| 4 | 2026-04-13 → 2026-04-29 | 17 days | Polish, video, group report, submission |

## 4. PERT-style task breakdown

Each task: id  duration(days)  predecessors  owner.

| ID | Task | Dur | Pred | Owner |
| --- | --- | --- | --- | --- |
| T1 | Define engine API contract | 2 | — | Floyd, Maysarah |
| T2 | Implement data models | 2 | T1 | Maysarah |
| T3 | Implement deck constants and helpers | 1 | T2 | Maysarah |
| T4 | Implement engine core (new_game, deal, next_turn) | 3 | T2, T3 | Maysarah |
| T5 | Pygame skeleton + ScreenManager | 2 | T1 | Floyd |
| T6 | Title-screen mockups + colour palette | 1 | T5 | Nasser |
| T7 | Unit tests F1–F3 | 2 | T4 | Abdurrahman |
| T8 | Implement Move / Suggest / Refute | 3 | T4 | Maysarah |
| T8b | Grid + dice movement (roll_die, legal_moves_for_roll, move_by_dice, board layout) | 3 | T4 | Floyd |
| T9 | Implement Accusation + win/lose | 2 | T8 | Maysarah |
| T10 | Setup, Game, End screens (with Human/AI toggle) | 4 | T5, T8, T8b | Floyd, Nasser |
| T11 | UI components (Button, PopupSelect, MessageBox) + Board renderer | 3 | T5 | Nasser |
| T12 | System tests F4–F8 | 2 | T9, T10 | Abdurrahman |
| T13 | Validation guards (wrong turn, eliminated, game-over) | 2 | T9 | Maysarah |
| T14 | F12 token-position fix | 1 | T13 | Maysarah |
| T14b | AI player module (ai.py, RandomAIPlayerStrategy, take_ai_turn, DetectiveNotes) and tests/test_ai.py | 2 | T13, T14 | Maysarah |
| T15 | UI polish (hover, end-screen, message log) | 2 | T10, T11 | Floyd, Nasser |
| T16 | validate_game_state, verify_deck | 1 | T14 | Maysarah |
| T17 | System tests F9–F16, NF2, F20–F23 | 2 | T13, T14, T14b, T16 | Abdurrahman |
| T18 | Final regression and code freeze | 1 | T15, T17 | Floyd, Abdurrahman |
| T19 | Demo video recording | 1 | T18 | Adam |
| T20 | Group report + peer review | 2 | T18 | Adam, all |
| T21 | Screenshots for README and system test report | 1 | T15 | Nasser |
| T22 | Submission ZIP assembly and integrity check | 1 | T19, T20, T21 | Adam, Floyd |

Critical path: T1 → T2 → T4 → T8 → T9 → T13 → T14 → T14b → T16 → T17 → T18 → T22. (T8b runs in parallel with T8 in Sprint 2; T14b runs in parallel with T16 in Sprint 3 because they touch different parts of the engine package.)

## 5. Resources

- Languages and runtime: Python 3.10+ (developed on 3.13).

- Libraries: pygame==2.6.1, pytest==9.0.3 (pinned in requirements.txt).

- Tooling: Git + GitHub for version control, Discord for async coordination, Google Meet for scheduled meetings, draw.io for diagrams.

- Hardware: developer laptops (Windows 11 primary).

- Time budget: approximately 120 person-hours total across the team over 9 weeks.

## 6. Plan vs actual

The plan was followed without scope cuts. The notable adjustments were:

- Grid + dice movement and the AI player were both kept in scope at the Sprint 2 midpoint meeting (2026-03-18) — the meeting that had been called as a candidate point to descope them. ADR-006 in docs/decisions.md records the rationale: marking-criteria leverage, identity of the Cluedo movement rule, and a judgement that the engineering risk was acceptable on the back of a frozen Sprint 1 engine API. Sprint 2 was extended by one week at the same meeting to absorb the integration work (planned 14 days, actual 21 days).

- The AI module was deferred from Sprint 2 to Sprint 3 to keep the Sprint 2 ambition focused on grid + dice and the human-player gameplay loop. The AI landed in Sprint 3 as a clean third consumer of the frozen engine API; the engine itself did not need to change to support it.

- F12 token-position bug was identified at the Sprint 3 midpoint (2026-04-08) and added to Sprint 3 scope; closed within the sprint with new unit tests covering "tokens move into room" and "tokens stay after refutation".

- Sprint 4 was strict freeze with one critical bugfix permitted (TC-25, the F12 visibility log line in the GUI's suggestion handler).

The shipped test count reflects the kept-in-scope decision: 116 unit tests passing at submission (33 from Sprint 1, ~30 added in Sprint 2, ~50 added in Sprint 3 covering F12 + validation + AI behaviour, stable at 113 through most of Sprint 4 with two additions during submission prep — a dice-fairness distribution test covering the spec §7 fair-dice integrity requirement and an engine-level guard against rolling twice in a single turn — bringing the final count to 116).