# Risk Register — Team 53

Risks are scored on a 1–3 scale (1 = low, 3 = high). Score = Likelihood × Impact. Anything scoring ≥ 6 was actively monitored at sprint reviews.

| ID | Risk | L | I | Score | Mitigation | Status at submission |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Engine / GUI integration breaks late | 2 | 3 | 6 | Engine API frozen in Sprint 1; integration smoke-test on every PR | Held; integration was clean from Sprint 2 |
| R2 | Pygame quirks on Windows | 2 | 2 | 4 | Use Pygame default font; develop on Windows; SDL_VIDEODRIVER=dummy in tests | Held; no platform issues |
| R3 | Scope creep (save/load, networked play, animations) | 3 | 2 | 6 | PO owns backlog; explicitly out-of-scope items refused at planning. Grid + dice and AI were kept in MVP scope at Sprint 2 midpoint (see ADR-006), not treated as scope creep — the team committed and delivered. | Held; no out-of-scope items shipped |
| R4 | Documentation gap at the end | 2 | 3 | 6 | DoD requires doc update each sprint; submission pack assembled progressively | Held; Sprint 4 had real polish budget |
| R5 | Team member inactive | 2 | 3 | 6 | Meeting notes record attendance; tasks reassignable each sprint | Mitigated; uneven attendance handled async via Discord |
| R6 | Tests rot as engine evolves | 1 | 2 | 2 | pytest -q gates every merge to main | Held; 116 tests green at submission |
| R7 | Marker cannot run the code | 2 | 3 | 6 | One-line install (pip install -r requirements.txt); README spells it out | Mitigated; instructions in README.md |
| R8 | Submission upload fails close to deadline | 2 | 3 | 6 | Adam to upload by 18:00 on 2026-04-28 — full 22-hour buffer before 4PM 30 April deadline | Mitigated; uploaded on time |
| R9 | Coursework clashes from other modules reduce attendance | 3 | 2 | 6 | Async work via Discord; written updates accepted in lieu of meeting attendance | Held; 3 members had reduced attendance, all delivered assigned tasks |

## Risks that fired

- R3 (scope creep) did not fire as a scope-creep risk. The Sprint 2 midpoint debate over grid + dice and AI was a deliberate scope decision — recorded in ADR-006 — not creep. The team committed to keep both in scope and absorb the cost (Sprint 2 extension, AI deferred to Sprint 3). No out-of-scope items (save/load, networked play, animations) made it into the codebase.

- R6 (tests rot) fired once during Sprint 3 when a fix to next_turn broke the elimination test. Caught on the next pytest run before merge.

- R9 (attendance) fired across the project. Adam (9/9) and Floyd (9/9) attended every meeting; Maysarah (8/9), Nasser (5/9), and Abdurrahman (4/9) had clashes. Mitigation worked: every member delivered their assigned tasks despite uneven meeting attendance.

No other risk fired with material impact.